## Gantt Chart
SPORTS COMPLEX MANAGEMENT SYSTEM (SCMS) — PROJECT GANTT CHART
Duration: August 2026 – December 2026 ¦ Project Lead: Jaspreet Singh ¦ Team: Jaspreet Singh, Sanveer Singh, Harshjot Singh ¦ Weekly Meeting: Every Monday
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | SPAN (WKS) | DARK WKS | DARK END | WEEKLY GANTT TIMELINE (WEEK NUMBER / WEEK-START DATE)
[9 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22
[9 empty] | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28
PHASE 1 — REQUIREMENTS & SCOPE |  | 100%
Requirements analysis | Jaspreet Singh | 100% | 2026-08-03 | 2026-08-04 | 2 | 1 | 1 | 2026-08-09
Business rules | Jaspreet Singh | 100% | 2026-08-03 | 2026-08-05 | 3 | 1 | 1 | 2026-08-09
Architecture scope | Sanveer Singh | 100% | 2026-08-04 | 2026-08-06 | 3 | 1 | 1 | 2026-08-09
Database/entity model | Harshjot Singh | 100% | 2026-08-05 | 2026-08-08 | 4 | 1 | 1 | 2026-08-09
API contract | Sanveer Singh | 100% | 2026-08-07 | 2026-08-09 | 3 | 1 | 1 | 2026-08-09
PHASE 2 — ARCHITECTURE & DATABASE DESIGN |  | 100%
FastAPI services | Sanveer Singh | 100% | 2026-08-10 | 2026-08-12 | 3 | 1 | 1 | 2026-08-16
SQLModel entities | Sanveer Singh | 100% | 2026-08-10 | 2026-08-13 | 4 | 1 | 1 | 2026-08-16
Alembic migrations | Sanveer Singh | 100% | 2026-08-12 | 2026-08-14 | 3 | 1 | 1 | 2026-08-16
Authentication | Jaspreet Singh | 100% | 2026-08-13 | 2026-08-15 | 3 | 1 | 1 | 2026-08-16
Fairness engine | Jaspreet Singh | 100% | 2026-08-14 | 2026-08-16 | 3 | 1 | 1 | 2026-08-16
Database/API consistency & documentation | Harshjot Singh | 100% | 2026-08-15 | 2026-08-17 | 3 | 2 | 2 | 2026-08-23
PHASE 3 — BACKEND FOUNDATION |  | 100%
FastAPI application | Sanveer Singh | 100% | 2026-08-17 | 2026-08-21 | 5 | 1 | 1 | 2026-08-23
PostgreSQL schema & seed data | Sanveer Singh | 100% | 2026-08-18 | 2026-08-23 | 6 | 1 | 1 | 2026-08-23
Authentication & core services | Sanveer Singh | 100% | 2026-08-20 | 2026-08-26 | 7 | 2 | 2 | 2026-08-30
Fairness allocation engine | Jaspreet Singh | 100% | 2026-08-22 | 2026-08-28 | 7 | 2 | 2 | 2026-08-30
Administrative APIs & verification | Harshjot Singh | 100% | 2026-08-24 | 2026-08-30 | 7 | 1 | 1 | 2026-08-30
PHASE 4 — WEB DASHBOARD |  | 90%
Admin dashboard | Sanveer Singh | 90% | 2026-08-24 | 2026-08-29 | 6 | 1 | 0
Inventory | Sanveer Singh | 90% | 2026-08-27 | 2026-09-01 | 6 | 2 | 1 | 2026-08-30
Slots | Sanveer Singh | 90% | 2026-08-29 | 2026-09-02 | 5 | 2 | 1 | 2026-08-30
Bookings & transactions | Sanveer Singh | 90% | 2026-08-30 | 2026-09-04 | 6 | 2 | 1 | 2026-08-30
Analytics & UI verification | Harshjot Singh | 90% | 2026-09-02 | 2026-09-06 | 5 | 1 | 0
PHASE 5 — FLUTTER MOBILE APPLICATIONS |  | 20%
Student app | Sanveer Singh | 20% | 2026-08-31 | 2026-09-06 | 7 | 1 | 0
Staff app | Sanveer Singh | 20% | 2026-09-02 | 2026-09-09 | 8 | 2 | 0
QR workflows | Jaspreet Singh | 20% | 2026-09-05 | 2026-09-10 | 6 | 2 | 0
Session handling | Jaspreet Singh | 20% | 2026-09-07 | 2026-09-11 | 5 | 1 | 0
Notifications | Harshjot Singh | 20% | 2026-09-09 | 2026-09-13 | 5 | 1 | 0
PHASE 6 — MOBILE INTEGRATION |  | 10%
Student E2E testing | Harshjot Singh | 10% | 2026-09-14 | 2026-09-18 | 5 | 1 | 0
Staff E2E testing | Harshjot Singh | 10% | 2026-09-14 | 2026-09-20 | 7 | 1 | 0
Fairness workflow validation | Jaspreet Singh | 10% | 2026-09-17 | 2026-09-22 | 6 | 2 | 0
Booking / QR integration | Sanveer Singh | 10% | 2026-09-19 | 2026-09-24 | 6 | 2 | 0
PHASE 7 — FULL SYSTEM INTEGRATION |  | 0%
Cross-platform workflow integration | Sanveer Singh | 0% | 2026-09-25 | 2026-09-30 | 6 | 2 | 0
Integration issue resolution | Jaspreet Singh | 0% | 2026-09-28 | 2026-10-03 | 6 | 1 | 0
Fairness validation | Jaspreet Singh | 0% | 2026-10-01 | 2026-10-06 | 6 | 2 | 0
Docker/runtime verification | Sanveer Singh | 0% | 2026-10-03 | 2026-10-08 | 6 | 2 | 0
Regression testing | Harshjot Singh | 0% | 2026-10-05 | 2026-10-10 | 6 | 1 | 0
PHASE 8 — DEPLOYMENT PREPARATION |  | 0%
Production secrets & configuration | Sanveer Singh | 0% | 2026-10-12 | 2026-10-16 | 5 | 1 | 0
Production database preparation | Sanveer Singh | 0% | 2026-10-15 | 2026-10-20 | 6 | 2 | 0
HTTPS configuration | Sanveer Singh | 0% | 2026-10-19 | 2026-10-22 | 4 | 1 | 0
Backup configuration | Jaspreet Singh | 0% | 2026-10-21 | 2026-10-24 | 4 | 1 | 0
Release configuration | Jaspreet Singh | 0% | 2026-10-26 | 2026-10-30 | 5 | 1 | 0
Production deployment | Jaspreet Singh | 0% | 2026-11-02 | 2026-11-06 | 5 | 1 | 0
Final acceptance testing | Harshjot Singh | 0% | 2026-11-09 | 2026-11-20 | 12 | 2 | 0
Final documentation | Harshjot Singh | 0% | 2026-11-23 | 2026-12-15 | 23 | 4 | 0
LEGEND
Dark Green = Completed portion (proportional to Progress %; full bar only at 100%)
Medium Green = 50-99% complete on a task that spans only one week (can't sub-divide a single cell)
Light Green = Remaining planned duration (100% of bar when Progress = 0%)
Red Vertical Line = Today
Formulas:
DARK END = IF([DARK WKS]=0,"",[START]-MOD([START]-J7,7)+7*[DARK WKS]-1)

## Project Details
PROJECT DETAILS — SPORTS COMPLEX MANAGEMENT SYSTEM (SCMS)
1. PROJECT OVERVIEW
Project Name | Sports Complex Management System (SCMS)
Project Objective | To design and deliver an integrated platform for managing a university sports complex — covering fair allocation of slots/inventory, bookings and transactions, staff/student mobile access, and administrative oversight — through a FastAPI backend, a web admin dashboard, and Flutter mobile apps.
Project Duration | August 2026 – December 2026
Project Lead | Jaspreet Singh
Weekly Meeting | Every Monday
2. TEAM MEMBERS & RESPONSIBILITIES
Jaspreet Singh (Team Leader) | System integration; requirements & scope definition; architecture review; authentication; fairness engine design; QR/session workflows; full system integration; final integration & deployment.
Sanveer Singh | Backend development (FastAPI, SQLModel, PostgreSQL, Alembic); REST APIs; web admin dashboard (inventory, slots, bookings & transactions); Flutter mobile app implementation; booking/inventory/transaction functionality; production infrastructure configuration.
Harshjot Singh | Requirements & workflow analysis; edge-case identification; database/entity consistency checks; API verification; analytics; data validation; UI and mobile (E2E) testing; fairness validation; regression testing; integration support; documentation; final acceptance testing.
3. PROJECT ROADMAP — PHASE SUMMARY
Phase | Status / Progress
Phase 1 — Requirements & Scope | Completed — 100%
Phase 2 — Architecture & Database Design | Completed — 100%
Phase 3 — Backend Foundation | Completed — 100%
Phase 4 — Web Dashboard | Nearly Completed — 90%
Phase 5 — Flutter Mobile Applications | In Progress — 20%
Phase 6 — Mobile Integration | In Progress — 10%
Phase 7 — Full System Integration | Upcoming — 0%
Phase 8 — Deployment Preparation | Upcoming — 0%
4. PHASE DESCRIPTIONS
Phase 1 | Gathered functional requirements, business rules, high-level architecture scope, the core database/entity model, and the API contract between frontend and backend.
Phase 2 | Designed the FastAPI service structure, SQLModel entity layer, Alembic migration strategy, authentication approach, and the fairness allocation engine concept.
Phase 3 | Built the backend foundation: the FastAPI application, PostgreSQL schema with seed data, authentication and core services, the fairness allocation engine, and administrative APIs.
Phase 4 | Delivered the web admin dashboard covering inventory, slot management, bookings & transactions, and analytics, with UI verification underway.
Phase 5 | Building the Flutter mobile applications for students and staff, including QR-based workflows, session handling, and notifications.
Phase 6 | Integrating the mobile applications with the backend and validating end-to-end student and staff flows, plus the fairness workflow.
Phase 7 | Full cross-platform (web + mobile + backend) system integration, resolution of integration issues, fairness validation, Docker/runtime verification, and regression testing.
Phase 8 | Preparation for production release: secrets/configuration management, production database setup, HTTPS, backups, release configuration, deployment, and final acceptance testing and documentation.
5. KEY ASSUMPTIONS
• | Task durations are estimated in calendar days and assume no major scope changes.
• | Progress percentages are self-reported by task owners at each weekly Monday meeting.
• | Phase 7 and Phase 8 task breakdowns were derived from the stated deliverables for those phases and are subject to refinement once Phase 6 completes.
• | The project assumes continuous team availability with no extended absences during Aug–Dec 2026.
• | Production deployment (Phase 8) targets completion within December 2026.
• | Because the Gantt renders at weekly granularity, the dark/light split per task is the nearest whole week-cell approximation of its Progress % — fully dark only at 100%, fully light at 0%.
6. STATUS SUMMARY
Overall Status | Phases 1–3 are complete. Phase 4 (Web Dashboard) is nearly complete at 90%. Phases 5–6 (mobile apps and mobile integration) are actively in progress. Phases 7–8 (full system integration and deployment preparation) are upcoming, scheduled to run through mid-December 2026.
Next Milestone | Complete mobile E2E testing (Phase 6) and begin full system integration (Phase 7).